## Sheet1
Seq. ID | Task | Task Owner | Notes
Migration Discovery
| Identify Servers and Databases | DBA
| Identify Owners of databases | DBA
| Identify applications of databases | SME
| Databases | SME
| Jobs | SME
| Logins | SME
| SSIS/DTS Packages | SME
| 3rd party app vs home grown | SME
| Is DTC Required? | SME
| What servers are required? | SME
| What special configurations are required? | SME | The next few items are examples of special configurations
MAXDOP
Collation
Required use of SA account
Physical drive usage instead of Mount points
| Test Plans | SME | This is very crucial. The SME has to think about this to understand what makes a migration successful from the application perspective.
| Linked servers | SME
| Security considerations | SME
| Firewall rules | SME
| Maintenance windows | SME
| Storage requirements | DBA/SME
| Replication | DBA
| Special Drivers installed on the SQL Server | SME
| Client connections | SME
| Third party backup solution | DBA
| DNS Entries | SME
Migration Preparation
| Run the Microsoft Upgrade Advisor against server | DBA
| Deliver report to owners | DBA
| Owners to review report and make necessary remediation changes to existing databases | SME
| Current database security is scripted and provided to owners | DBA
| Security to be remediated to least privilege required for each login | DBA/SME
| Security to be cleaned up removing excess logins and permissions | DBA/SME
| Request server builds | DBA
| Install and configure SQL Server in accordance to TSS and SOE | DBA
| Configure SQL Server in accordance to discovery requirements | DBA
| Configure SQL Server in accordance to DBA standards | DBA
| DTS/SSIS packages converted to new version | SME
| How many availability groups are required | DBA/SME
| Request IP Addresses for each Availability Group | DBA
Migration Week
| Logins scripted and created on target server | DBA
| Jobs scripted and created on target server | DBA
| Script database permissions | DBA
| SSIS Packages deployed to SQL Server | DBA/SME
| Dummy databases created to initialize Availability Groups | DBA
| Backup all source databases scoped in migration | DBA
| Shrink transaction log files | DBA
| Restore all source databases to target server leaving in NO RECOVERY | DBA
| Firewall rules | DBA/SME
| Dry Run | DBA/SME
| Communications to user community | SME
Migration Day
| Communications to user community | SME
| Shrink transaction log files | DBA
| Set all source databases to read only | DBA
| Take final differential backup of source databases | DBA
| Set all source databases offline | DBA
| Restore all source databases to target server leaving WITH RECOVERY | DBA
| Drop all users from restored database | DBA
| Assign remediated security to databases | DBA
| Set all databases on target server to read write | DBA
| Set owner of database to SA or renamed SA Account | DBA
| Set Compatibility Level to latest version allowed | DBA
| Run DBCC UPDATEUSAGE against database | DBA
| Run DBCC CHECKDB WITH DATA PURITY against database | DBA
| Rebuild all indexes | DBA
| Update all statistics | DBA
| Recompile all stored procedures | DBA
| Add databases to appropriate availability groups | DBA
| Assign listener names to availability groups | DBA
| DBA Team signs of on migration | DBA
| Database owner Team commences testing | SME
| Database owner team signs off on testing | SME
| Communications to user community | SME